## Milestones
Milestone | WP ID | Task | Output Artifact | Source / Depends On | Status
M0 — Foundations (Week 1, in progress) | M0.1 | Register Kawasaki source files in data/references.csv | data/references.csv (5 source rows) | sources/raw/ Kawasaki files | ✅
| M0.2 | Lock kickoff decisions D1–D4 (basis, platform, scope, NH3 policy) | Locked-decisions table in 00-milestones.md | Kickoff Q&A | ✅
| M0.3 | Create OKR file (docs/okr.md) and granular milestone plan (00-milestones.md); wire CLAUDE.md to OKR | docs/okr.md, docs/comparison/00-milestones.md | — | ✅
| M0.4 | Define KR1.1 DB schema: column names, units, cost-year, id-link rule for data/costs/, data/vessels/, data/properties/ | data/README.md (data dictionary) | docs/conventions.md | ⬜
| M0.5 | User approval of milestone plan | Sign-off | User | 🔒
M1 — KR1.1: LH2 Techno-Economic DB v1 (Weeks 2–4) | M1.1 | Liquefaction params: SEC 8–9 kWh/kg & 0.55 kWh/Nm³, unit cap 115 t/d, min scale ~10 000 tpa, H2 Claude + N₂ precool, O–P catalyst (Fe-based), no degradation | data/properties/liquefaction.csv | kawasaki-2026-questionnaire, -supplemental · M0.4 | ⬜
| M1.2 | Export/loading terminal: BOR 0.1 %/d, 64 000 m³/tank ×3–4, dead-volume (≈ LNG, NPSHr-driven), downstream BOG reliquefaction | data/properties/terminals.csv | kawasaki-2026-supplemental, -questionnaire | ⬜
| M1.3 | Shipping vessel specs: 160 000 m³ @ 29.6 km/h (16 kn), 40 000 m³ (building), Suiso Frontier 1 250 m³, BOG-as-fuel = BOR, no onboard reliquefaction, port time 1–1.5 days | data/vessels/lh2-carriers.csv | kawasaki-2026-supplemental, -questionnaire | ⬜
| M1.4 | Receiving terminal + regas: BOR 0.1 %/d, 65 000 m³/tank, ORV/seawater vaporiser, heat duty 3.8 MJ/kg-LH2 | data/properties/regas.csv | kawasaki-2026-questionnaire | ⬜
| M1.5 | Cost stack table: IAE per-component USD breakdown for LH2 Base / Large / Tech (liquefier, loading terminal, seaborne transport, receiving terminal, regas). ⚠ KHI withholds CapEx/OpEx in $/kg — IAE stack is the only quantitative basis | data/costs/lh2-cost-stack.csv | kawasaki-2026-supplemental → iae-2019-gigaton | ⬜
| M1.6 | LH2 physical properties: NBP ≈ 20.3 K, density ≈ 70.8 kg/m³, LHV 120 MJ/kg, HHV 142 MJ/kg — each cited | data/properties/lh2-properties.csv | docs/conventions.md + cited refs | ⬜
| M1.7 | Data dictionary: column definitions, units, cost-year tagging rule, id-link convention | data/README.md | M0.4 | ⬜
| M1.8 | Validation: smoke test loads every table, asserts no untagged numbers, cost-stack components reconcile to totals | tests/test_data_tables.py | M1.1–M1.6 | ⬜
M2 — KR1.2: LH2 Shipping Functional-Requirements Spec (Weeks 3–5, parallel to M1) | M2.1 | Capture existing ammonia model I/O structure (tabs, inputs, outputs, formula style) to mirror | Notes section in spec | User (ammonia spreadsheet model) | 🔒
| M2.2 | Define INPUTS: cargo size, route distance, speed, BOR, fuel logic, port/turnaround times, fleet & availability params, vessel CapEx/charter rate | Spec §Inputs | M1.3 | ⬜
| M2.3 | Define CALCULATION LOGIC / FORMULAS: voyage time, laden+ballast BOG, BOG-as-fuel (fuel = BOR), MGO shortfall, in-transit losses, fleet sizing, annual delivered kg | Spec §Logic | kawasaki-2026-questionnaire | ⬜
| M2.4 | Define OUTPUTS: shipping cost $/kg delivered, fleet count, boil-off loss %, energy/voyage, CO₂ emissions | Spec §Outputs | M2.3 | ⬜
| M2.5 | LH2-vs-NH3 modelling DELTAS the spreadsheet must add: no onboard reliquefaction, cryogenic BOR regime, volumetric/density basis, dual-fuel BOG engine, KHI 'no H2 loss' treatment | Spec §LH2-vs-NH3 Deltas | kawasaki-2026-questionnaire, -comparison | ⬜
| M2.6 | Worked example / validation case: sample voyage for model team to cross-check | Spec §Worked Example | M2.2–M2.4 | ⬜
| M2.7 | Handover review with model team; incorporate feedback | Reviewed spec v1 (docs/comparison/lh2-shipping-functional-requirements.md) | User / model team | ⬜
M3 — KR1.3: LH2-vs-NH3 Comparison (Weeks 5–8) | M3.1 | LH2 chain cost stack → LCOH ($/kg delivered) on generic basis (Base 2.5B Nm³/y & Large 10B Nm³/y) | Memo §Economics (LH2); data/costs/ | M1.5; economics.lcoh() | ⬜
| M3.2 | NH3 chain cost stack → LCOH (incl. synthesis, shipping, cracking/reconversion) | Memo §Economics (NH3); data/costs/ | User internal NH3 dataset (D4) — BLOCKED | 🔒
| M3.3 | BOG / boil-off comparison across full chain (loading terminal + voyage + receiving terminal) | Memo §BOG | M1; NH3 data | ⬜
| M3.4 | Speed / voyage time on existing vessels (LH2 16 kn vs NH3 carrier) | Memo §Speed | M1.3; NH3 data | ⬜
| M3.5 | End-to-end energy consumption (liquefaction SEC vs NH3 synthesis + cracking, regas) | Memo §Energy | M1.1, M1.4; NH3 data | ⬜
| M3.6 | Complexity / TRL + safety / permitting (toxicity, safety separation distances, loading-arm TRL 6–7, ammonia hazard abatement vs LH2 separation) | Memo §Complexity | kawasaki-2026-questionnaire, -comparison | ⬜
| M3.7 | Sensitivities on dominant drivers (scale, distance, energy price) | Memo §Sensitivity | M3.1–M3.2 | ⬜
| M3.8 | Corridor re-run (D1): re-run full comparison on named origin → destination, distance, annual volume | Memo Addendum | User corridor inputs (D1) — BLOCKED | 🔒
| M3.9 | Final comparison memo write-up + go/no-go read: boundary, units, cost-year, assumptions up front; Sources list at end | docs/comparison/lh2-vs-nh3.md | M3.1–M3.7 | ⬜